## Cover
Document | DARS UK COPO LENS-LRMS draft
Source | docs/uat/UAT-UKCOPO-LRMS.md (full markdown narrative, decision trees & cross-refs)
Companion | docs/uat/UAT-UKCOPO-LRMS-DecisionTrees.docx (decision-tree narrative)
Generated | 2026-06-01 20:53:27
Total tests | 34
Family 1 | 3 tests
Family 2 | 19 tests
Family 3 | 7 tests
Smoke tests | 5 tests
Sheet layout | Each test case is a stacked block: 3 metadata rows + 1 column-header row + N step rows + 1 blank separator.
Pass/Fail enum | Pass · Fail · Blocked · Not Run (data validation on the Pass/Fail? column).
Tester rows | Empty — tester to fill in.
Step rows | Pre-populated with the action ("Steps To Perform Test") and the matching "Expected Results" — both pulled verbatim from the source markdown.

## Test Cases
UAT-UKCOPO-LRMS-001 · UK COPO via Court Order — end-to-end Triage → Resolved
Case: LNS-2025-555444 · Persona: TS (primary, Triage), RS (secondary, Fulfillment/Publish) · Stage: Triage · Waiting on Triage → Fulfillment · InProgress → Publish · PublishInProgress → Publish · Resolved · Case shape: United Kingdom / International / Court Order · 1+ Consumer identifier(s) · seeded from `mockCaseApi.MOCK_CASES`
Capability validated: Full LRMS walk for the canonical UK COPO case — country=United Kingdom + `authorizationType="Court Order"` — exercising every WorkflowStage (Triage → Fulfillment → Publish) and every terminal `WorkflowState=Resolved` transition. Verifies the seed mock case (`mockCaseApi.ts` line 849) renders correctly and that each stage advances via the documented trigger.
Preconditions: (1) Default queue; mock backend on. (2) UK seed case `LNS-2025-555444` is present in `mockCaseApi.MOCK_CASES` with `country="United Kingdom"`, `agency.agencyName="Metropolitan Police Service"`, `authorizations[0].authorizationType="Court Order"`, `authorizations[0].authorizationNumber="UK-2025-CO-789"`, `authorizations[0].issuingAuthority="Westminster Magistrates' Court"`, `regulatoryCompliance.regulationType="CLOUD Act"`, `regulatoryCompliance.applicableLaws=["UK Terrorism Act 2000"]`, `regulatoryCompliance.reviewStatus="Approved"`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | From the browser, navigate to ` https://ppe.dars.lens.microsoft.com`. The Case Queue list renders. |  | `/cases` queue mounts; UK seed case row is visible.
2 | In the Case Queue, locate the row whose Case ID column reads `LNS-2025-555444`. Click that row. The Case Details page mounts at `/cases/LNS-2025-555444`. |  | Case Details page mounts at `/cases/LNS-2025-555444`.
3 | At the top of the page, observe the `WorkflowSidebar` on the left edge (collapsed by default). Click the chevron toggle button at the top of the rail (aria-label "Expand workflow sidebar"). The sidebar expands and shows three stage rows: "Triage" (active), "Fulfillment" (available/disabled), "Collection, Prep & Delivery" (available/disabled). |  | `WorkflowSidebar` expands; Triage stage is active.
4 | Immediately below the sidebar's top toggle, find the `TriageStepsBanner` at the top of the main content column. Verify the banner title reads `Triage Quick Steps` and a primary action button labelled **Complete Triage** is visible (likely disabled at this point — hover over it to reveal the tooltip listing the unmet gates). |  | `TriageStepsBanner` reads `Triage Quick Steps`; **Complete Triage** button is disabled with a tooltip listing unmet gates.
5 | Directly below the `TriageStepsBanner`, find the `CaseInfoBar`. Verify the case number reads `LNS-2025-555444`, the agency reads `Metropolitan Police Service`, and the workflow state pill reads `Waiting on Triage`. |  | `CaseInfoBar` reads case number `LNS-2025-555444`, agency `Metropolitan Police Service`, state pill `Waiting on Triage`.
6 | In the main content column, scroll until you see the numbered section group `2. Legal & Compliance`. If the group is collapsed (the chevron on the right of the group header points down), click the group header to expand it.
7 | Inside Section 2, find the inner `LegalClassificationSection` Accordion (left column of the two-column grid). If its accordion chevron is closed, click the accordion header to open it. Locate the `Country` dropdown. Verify the selected value reads `United Kingdom`. |  | `LegalClassificationSection` `Country` dropdown reads `United Kingdom`.
8 | Locate the `Jurisdiction` field directly next to `Country`. Verify it reads `International`. |  | `Jurisdiction` reads `International`.
9 | Still in Section 2, scroll past the two-column grid to the full-width `RegulatoryComplianceSection` accordion below. Click its header (GlobeRegular icon) to expand. Verify: |  | `RegulatoryComplianceSection` shows `CLOUD Act` / `UK Terrorism Act 2000` / `Approved`; EU27 harms hidden; Shield Law hidden.
10 | Scroll to the numbered section group `4. Identifier & Data Services`. If collapsed, click the group header chevron to expand it. The inner `AccountIdentifiersSection` accordion (defaultOpenItems=['accountIdentifiers']) should already be open.
11 | At the top of the section, find the Add-Identifier form (Identifier Type select, Identifier Value input, **Add** button). Pick `Email` from the Type dropdown, type `cfo@kontoso-uk.example` into the Value input. The required tri-column appears below: pick `cfo@kontoso-uk.example` in the "Linked LE Identifier" dropdown, pick `Outlook` in the "Associated Service" dropdown, pick `Basic Subscriber Info` in the "Data Categories" dropdown. Click **Add**. A toast confirms the identifier was added; the identifiers table at the bottom of the section now shows a new row. |  | Identifier row appears in the table with Status `Pending`.
12 | Above the identifiers table, click **Check Accounts** (or **Re-check Accounts** if already run). Wait for the per-row Status column to update from `Pending` to `Found` (or `Blocked` if the mock returns a CLASS hit). For UK COPO, expect `Found`. The button text flips to **Re-check**. |  | Status flips to `Found`; button reads `Re-check Accounts`.
13 | Click the chevron on the right edge of the row for `cfo@kontoso-uk.example`. The row expands inline showing a Consumer profile bar (country, email, displayName) and a services sub-table. Verify the services sub-table contains an `Outlook` row with a Categories count of `1`. |  | Expanded row shows Consumer profile + Outlook service with Categories count `1`.
14 | Scroll back up to the `TriageStepsBanner`. Hover over the **Complete Triage** button. If the tooltip lists unmet gates (assignee, priority, nature of crime, regulatory review), resolve each one: |  | Each remediation step removes the corresponding gate from the **Complete Triage** tooltip.
15 | Click **Complete Triage**. The page advances: the `TriageStepsBanner` title changes to `Fulfillment Steps`, the `WorkflowSidebar` advances the active marker from Triage to Fulfillment, and the `CaseInfoBar` workflow state pill reads `In Progress` under Fulfillment. |  | `TriageStepsBanner` title reads `Fulfillment Steps`; sidebar active marker moves; state pill reads `In Progress`.
16 | Scroll down to Section 4 (`AccountIdentifiersSection`). At the bottom of the section, click the **Open Fulfillment Wizard** primary footer button. The page navigates to `/cases/LNS-2025-555444/fulfillmentwizard` and mounts `FulfillmentWizardView`. |  | Route changes to `/cases/LNS-2025-555444/fulfillmentwizard`; `FulfillmentWizardView` mounts; Step 1 is active.
17 | Step 1 of the wizard mounts — `IdentifierReviewStep`. Verify the identifier row for `cfo@kontoso-uk.example` is shown. Click the **Next** button in the `WizardFooter`. The wizard advances to Step 2 — `ServicesConfigurationStep`. |  | Step 1 shows the identifier; **Next** advances to Step 2.
18 | In Step 2, the default mode is Bulk. In the `DataCollectionPeriod` card at the top, pick a start date of `2026-01-01` and an end date of `2026-04-22`. Below, in the `MicrosoftServicesList`, tick the `Outlook` service row and confirm `Basic Subscriber Info`, `Authentication Logs`, `Content` are ticked. |  | `DataCollectionPeriod` reflects the chosen dates; `MicrosoftServicesList` `Outlook` row shows the three category checkmarks.
19 | Click **Next** in the `WizardFooter`. The wizard advances to Step 3 — `FulfillmentPlanReviewStep`. Verify the `ChangesSummary` card lists the identifier and that the summary tile `Date Range` reads `Jan 1, 2026 – Apr 22, 2026`. |  | Step 3 `ChangesSummary` lists the identifier; `Date Range` summary tile reads `Jan 1, 2026 – Apr 22, 2026`.
20 | Click **Save** (or **Submit**) in the `WizardFooter`. A toast confirms `Fulfillment plan saved`; the browser navigates back to `/cases/LNS-2025-555444`. |  | Save toast renders; navigation returns to `/cases/LNS-2025-555444`.
21 | On the Case Details page, scroll to the `BottomActionBar` at the bottom of the page. Click **Submit Fulfillment**. The `FulfillmentSummaryDialog` opens summarising identifier count, service count, date range. Click **Submit** in the dialog. |  | `FulfillmentSummaryDialog` shows the plan summary; **Submit** is enabled.
22 | The page transitions: the `WorkflowSidebar` active marker advances to "Collection, Prep & Delivery"; the route `/cases/LNS-2025-555444` now renders `CollectionPrepDeliveryPage` (because `workflowStage === WorkflowStage.Publish`). At the top of the page, the `CollectionPageHeader` renders with a Database24Regular icon, title, and two buttons: **Check Job Status** + **Resolve Case**. |  | Route renders `CollectionPrepDeliveryPage`; `CollectionPageHeader` shows the two buttons.
23 | Below `CollectionPageHeader`, observe the `FulfillmentPipelineCard` showing three columns: Collection / Prepare / Delivery, each with a 0/N progress bar. |  | `FulfillmentPipelineCard` shows three phase columns.
24 | Below the pipeline card, observe the `CollectionTabBar` (All / Needs Action / By Identifier / Complete). Click `All`.
25 | Scroll to the `FulfillmentTrackerSection`. Click the identifier row to expand. Per-service `CategoryStatusTable` rows render. For each row where the Phase Status badge reads `Ready to Submit` (or the collection job has completed), click the **Submit** action in the Actions column. |  | Per-row **Submit** action moves Collection→Prepare.
26 | After all categories are submitted, the per-row Phase Status badges advance to `Ready to Deliver`. For each row, click **Deliver**. |  | Per-row **Deliver** action moves Prepare→Delivery.
27 | Once all rows show `Delivered` and the `FulfillmentPipelineCard` Delivery column reads `N/N`, scroll back to the `CollectionPageHeader`. Click **Resolve Case**. The `ResolveCaseDialog` modal opens. |  | `ResolveCaseDialog` modal opens with `Resolution Status` defaulted to `Resolved`.
28 | In the dialog, verify the default `Resolution Status` dropdown is set to `Resolved`. Type a brief note into the `Resolution Notes` textarea (e.g. "All requested categories delivered to Metropolitan Police Service per Westminster Magistrates' Court order UK-2025-CO-789"). Click **Resolve Case**. A success toast renders; the dialog closes; the `CaseInfoBar` workflow state pill reads `Resolved`. |  | Success toast `"Case Resolved"`; dialog closes; state pill reads `Resolved`.
29 | Scroll to Section 6 — `Operational Case Review`. If collapsed, click the group header chevron. The inner `OperationalReviewCard` Accordion is default-open. Under the `All` tab, verify at minimum these note rows are present (chronological, newest-first): a Triage-stage note created during Triage QC (per spec `case-stage-state-audit-logging.md`), the Fulfillment plan save event, the Submit Fulfillment event, the Resolve Case note text from Step 28. |  | Notes timeline shows at least the user-written Resolve note.
30 | **Note (spec gap)**: Per discovery, the WebClient does not currently auto-emit audit log entries on stage transitions — only user-written notes appear here. If only the Step 28 note is visible, log a structural FAIL referencing `case-stage-state-audit-logging.md` and the empty auto-audit surface area. |  | If auto-audit entries are missing, the structural gap is logged against `case-stage-state-audit-logging.md`. Pass criteria: • Every Part A–H expected result is observable. • The case lands at `WorkflowState=Resolved` after the dialog completes. • The notes timeline carries the user-written events (auto-audit is N/A per spec gap).
UAT-UKCOPO-LRMS-002 · UK COPO via Subpoena — end-to-end Triage → Resolved
Case: UKCOPO-LRMS-SUBPOENA-SYNTH · Persona: TS (primary), RS (secondary) · Stage: Triage · Waiting on Triage → Publish · Resolved · Case shape: United Kingdom / International / Subpoena · 1 Consumer identifier · synthesised
Capability validated: Same end-to-end walk as UAT-UKCOPO-LRMS-001 but with `authorizationType="Subpoena"` — proves that the LRMS state machine is independent of authorizationType (UK COPO can be modelled as any of the three UK-applicable AuthorizationType enum members from `domain.constants.ts` line 29-37).
Preconditions: (1) Seed `UKCOPO-LRMS-SUBPOENA-SYNTH` into `mockCaseApi.MOCK_CASES` by cloning `LNS-2025-555444` and overriding: `caseId="UKCOPO-LRMS-SUBPOENA-SYNTH"`, `authorizations[0].authorizationType="Subpoena"`, `authorizations[0].authorizationNumber="UK-2025-SUB-456"`, `authorizations[0].issuingAuthority="Crown Prosecution Service"`. (2) Default queue.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases`. Click the row for `UKCOPO-LRMS-SUBPOENA-SYNTH`. The Case Details page mounts.
2 | Scroll to Section 3 — `Sender Authority Details`. Click the group chevron to expand. Click the inner `AuthorizationsSection` accordion header. Verify the first authorization row reads `Authorization Type: Subpoena`, `Authorization Number: UK-2025-SUB-456`, `Issuing Authority: Crown Prosecution Service`. |  | `Subpoena` authorization renders in Section 3.
3 | Follow Parts B–H of UAT-UKCOPO-LRMS-001 verbatim. The state machine behaviour is identical.
UAT-UKCOPO-LRMS-003 · UK COPO via Administrative Subpoena — end-to-end Triage → Resolved
Case: UKCOPO-LRMS-ADMINSUBP-SYNTH · Persona: TS (primary), RS (secondary) · Stage: Triage · Waiting on Triage → Publish · Resolved · Case shape: United Kingdom / International / Administrative Subpoena · 1 Consumer identifier · synthesised
Capability validated: Same end-to-end walk with `authorizationType="Administrative Subpoena"` — proves the third UK-applicable AuthorizationType enum value behaves identically.
Preconditions: (1) Seed `UKCOPO-LRMS-ADMINSUBP-SYNTH` into `mockCaseApi.MOCK_CASES` by cloning `LNS-2025-555444` and overriding: `caseId="UKCOPO-LRMS-ADMINSUBP-SYNTH"`, `authorizations[0].authorizationType="Administrative Subpoena"`, `authorizations[0].authorizationNumber="UK-2025-ADM-321"`, `authorizations[0].issuingAuthority="UK Home Office"`. (2) Default queue.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases`. Click the row for `UKCOPO-LRMS-ADMINSUBP-SYNTH`. The Case Details page mounts.
2 | Scroll to Section 3 — `Sender Authority Details`. Expand the group + inner `AuthorizationsSection` accordion. Verify the first authorization row reads `Authorization Type: Administrative Subpoena`, `Authorization Number: UK-2025-ADM-321`, `Issuing Authority: UK Home Office`. |  | `Administrative Subpoena` authorization renders in Section 3.
3 | Follow Parts B–H of UAT-UKCOPO-LRMS-001 verbatim.
UAT-UKCOPO-LRMS-100 · Intake/Triage `WaitingOnTriage` → `InProgress` (assign)
Case: UKCOPO-LRMS-TRANS-100 · Persona: TS · Stage: Triage · WaitingOnTriage → Triage · InProgress · Case shape: United Kingdom / International / Court Order · 1 Consumer identifier · synthesised
Capability validated: `useWorkflowActions.assign(assigneeName)` flips `WorkflowState` from `WaitingOnTriage` to `InProgress` while keeping `WorkflowStage` in Triage. Verifies the assignment surface in `AssignedToCard` writes the assignee via the Redux/API path and that the `CaseInfoBar` state pill updates.
Preconditions: (1) Seed `UKCOPO-LRMS-TRANS-100` from `LNS-2025-555444` with `workflowStage="Triage"` and `workflowState="WaitingOnTriage"`, `assigneeName=null`. (2) Default queue.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases`. Click the row for `UKCOPO-LRMS-TRANS-100`. Case Details mounts.
2 | Verify the `CaseInfoBar` state pill reads `Waiting on Triage` and the Assignee chip (right side of the bar) reads `Unassigned`. |  | State pill `Waiting on Triage`; Assignee chip `Unassigned`.
3 | Scroll to Section 1 — `Case Overview`. If collapsed, click the group chevron to expand. In the right sidebar column inside Section 1, find the `AssignedToCard`. Click the **Assign to me** shortcut button at the top of the card. The card updates: the assignee combobox now shows the current user's display name. |  | `AssignedToCard` assignee field shows the current user.
4 | Wait 1–2s for the autosave indicator in `CaseInfoBar` to flip from "Saving…" to "Last saved …". |  | Autosave completes ("Last saved …" timestamp updates).
5 | Re-inspect the `CaseInfoBar` state pill. |  | State pill flips to `In Progress`; Assignee chip in `CaseInfoBar` updates to the current user.
6 | Scroll to Section 6 — `Operational Case Review` → expand → click the **All** tab. |  | Per spec, an `AssigneeUpdated` / `TriageStarted` audit note should appear. **If absent**, log structural FAIL referencing `case-stage-state-audit-logging.md`. Pass criteria: • State transitions `WaitingOnTriage → InProgress`. • Stage stays `Triage`. • Assignee written. • Notes timeline carries the event (or structural FAIL logged if the auto-emit gap exists).
UAT-UKCOPO-LRMS-101 · Triage `InProgress` → Fulfillment `InProgress` (triageComplete)
Case: UKCOPO-LRMS-TRANS-101 · Persona: TS · Stage: Triage · InProgress → Fulfillment · InProgress · Case shape: United Kingdom / International / Court Order · 1 Consumer identifier · synthesised, mid-triage
Capability validated: `useWorkflowActions.triageComplete()` advances the case from Triage stage to Fulfillment stage, with state remaining `InProgress`. Verifies the canCompleteTriage gate (`useWorkflowTransitions.ts:73-82`) honours the UK requirement (`isUnitedKingdom(country) ⇒ requiresRegulatoryReview = true`).
Preconditions: (1) Seed `UKCOPO-LRMS-TRANS-101` from `LNS-2025-555444` with `workflowStage="Triage"`, `workflowState="InProgress"`, `assigneeName=<TS user>`, `casePriority="High"`, `natureOfCrime=["Terrorism"]`, `regulatoryCompliance.reviewStatus="Approved"`. (2) Default queue.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-TRANS-101`. Case Details mounts.
2 | Verify the `CaseInfoBar` state pill reads `In Progress` under stage `Triage` (the sidebar's Triage stage is active). |  | State pill `In Progress`; sidebar Triage active.
3 | Scroll to the `TriageStepsBanner` at the top. Hover over the **Complete Triage** button — verify the tooltip is empty (no unmet gates). |  | **Complete Triage** is enabled (no tooltip gates).
4 | Click **Complete Triage**. |  | Button click fires `useWorkflowActions.triageComplete()`.
5 | Wait ~1s. Observe the page chrome. |  | `TriageStepsBanner` title flips to `Fulfillment Steps`; `WorkflowSidebar` active marker advances to Fulfillment; state pill still reads `In Progress` (under Fulfillment stage).
6 | Scroll to Section 6 → expand → **All** tab. |  | Per spec, `TriageCompleted` audit note should appear; if absent, log structural FAIL. Pass criteria: • Stage advances Triage→Fulfillment. • State remains `InProgress`. • Banner/title and sidebar update. • Notes timeline carries the event (or structural FAIL).
UAT-UKCOPO-LRMS-102 · Triage `InProgress` → Fulfillment `RecommendRejection`
Case: UKCOPO-LRMS-TRANS-102 · Persona: TS · Stage: Triage · InProgress → Fulfillment · RecommendRejection · Case shape: United Kingdom / International / Court Order · 1 Consumer identifier · synthesised, mid-triage
Capability validated: `useWorkflowActions.recommendRejection(reason)` writes a Rejection note FIRST (throws if the note write fails) then transitions stage Triage→Fulfillment and state to `RecommendRejection`. Verifies the reason-text requirement and the side-effect ordering documented at `useWorkflowActions.ts:75-131`.
Preconditions: (1) Seed `UKCOPO-LRMS-TRANS-102` from `LNS-2025-555444` with `workflowStage="Triage"`, `workflowState="InProgress"`, assigned to a TS user.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-TRANS-102`. Case Details mounts.
2 | Scroll to the `CaseDetailsFooter` at the bottom of the page. Click **Recommend Rejection**. The `RecommendRejectionDialog` modal opens. |  | `RecommendRejectionDialog` opens.
3 | In the dialog, leave the Reason textarea empty. Click **Submit**. Verify the dialog blocks submit with a validation error like "Reason required" (form-level guard before the API call). |  | Empty reason rejected with validation error; API not called.
4 | Type `UK COPO order outside Microsoft scope — Westminster Magistrates' Court order targets non-Microsoft service.` into the Reason textarea. Click **Submit**. |  | Submit fires `recommendRejection(reason)`.
5 | The dialog closes. Inspect the chrome. |  | State pill reads `Recommend Rejection`; sidebar advances stage to Fulfillment; banner reads `Fulfillment Steps`.
6 | Scroll to Section 6 → expand → **All** tab. |  | A Rejection note row appears at the top of the timeline with type `Rejection`/`Triage` and the reason text body. Pass criteria: • Empty reason blocked. • Non-empty reason: state→`RecommendRejection`, stage→`Fulfillment`, Rejection note persisted.
UAT-UKCOPO-LRMS-103 · Fulfillment `RecommendRejection` → `Rejected` (finalizeRejection)
Case: UKCOPO-LRMS-TRANS-103 · Persona: RS · Stage: Fulfillment · RecommendRejection → Fulfillment · Rejected · Case shape: United Kingdom / International / Court Order · 1 Consumer identifier · synthesised, post-recommend
Capability validated: `useWorkflowActions.finalizeRejection(reason)` from `RecommendRejection` state — `canFinalizeRejection` is true when `isFulfillmentStage AND (state == RecommendRejection ¦¦ Rejected) AND rejectionReason present`. Writes a Rejection note then transitions state to `Rejected` (terminal).
Preconditions: (1) Seed `UKCOPO-LRMS-TRANS-103` from `LNS-2025-555444` with `workflowStage="Fulfillment"`, `workflowState="RecommendRejection"`, `rejectionReason="Set by TS during triage"`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-TRANS-103`. Case Details mounts (Fulfillment-stage view).
2 | Verify the `CaseInfoBar` state pill reads `Recommend Rejection`. |  | State pill `Recommend Rejection`.
3 | Scroll to `CaseDetailsFooter`. Click **Finalize Rejection** (only visible when `canFinalizeRejection`). The `FinalizeRejectionDialog` opens. |  | `FinalizeRejectionDialog` opens.
4 | Type a finalize reason: `RS concurs with TS rejection — closing case.` Click **Submit**.
5 | The dialog closes. Inspect chrome. |  | State pill reads `Rejected`; the case becomes read-only (`isReadOnly === true` because `Rejected` is in `END_STATES`); footer destructive buttons disappear or disable.
6 | Scroll to Section 6 timeline. |  | A second Rejection note appears with the finalize reason. Pass criteria: • State `Rejected` reached. • Case becomes read-only. • Two Rejection notes recorded (TS recommend + RS finalize).
UAT-UKCOPO-LRMS-104 · Fulfillment `InProgress` → `Rejected` (direct finalize)
Case: UKCOPO-LRMS-TRANS-104 · Persona: RS · Stage: Fulfillment · InProgress → Fulfillment · Rejected · Case shape: United Kingdom / International / Court Order · 1 Consumer identifier · synthesised
Capability validated: From the same `useWorkflowActions.finalizeRejection(reason)` path, this time without first passing through `RecommendRejection` — proves the gate `state == RecommendRejection ¦¦ Rejected` is permissive enough to skip the intermediate step when RS pre-sets the state, or that the dialog accepts a direct rejection. (Per `useWorkflowTransitions.ts`, `canFinalizeRejection` requires `state == Rejected ¦¦ RecommendRejection`; if the dialog refuses, this is the expected branch and the test logs N/A.)
Preconditions: (1) Seed `UKCOPO-LRMS-TRANS-104` from `LNS-2025-555444` with `workflowStage="Fulfillment"`, `workflowState="InProgress"`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-TRANS-104`.
2 | Scroll to `CaseDetailsFooter`. If a **Finalize Rejection** button is visible, click it. Otherwise (per gate semantics, this button may be hidden because `state==InProgress` not `RecommendRejection`), the path is via `RecommendRejection` first — in that case, mark this test N/A and rerun UAT-UKCOPO-LRMS-102→103. |  | Either (a) button visible → proceed to Step 3, or (b) button hidden → N/A, fall back to 102+103 chain.
3 | If the button was visible: in the dialog, supply a reason `Direct rejection by RS after review.` Click **Submit**. |  | Pass criteria: • Either the direct path works and lands at `Rejected`, OR the gate correctly hides the button and the test is N/A (in which case 103 covers the path).
UAT-UKCOPO-LRMS-105 · Fulfillment `InProgress` → `Withdrawn`
Case: UKCOPO-LRMS-TRANS-105 · Persona: RS · Stage: Fulfillment · InProgress → Fulfillment · Withdrawn · Case shape: United Kingdom / International / Court Order · 1 Consumer identifier · synthesised
Capability validated: `useWorkflowActions.withdraw()` flips state to `Withdrawn` (terminal) without changing stage. Verifies the `!isReadOnly` gate and the WithdrawConfirmationDialog flow.
Preconditions: (1) Seed `UKCOPO-LRMS-TRANS-105` from `LNS-2025-555444` with `workflowStage="Fulfillment"`, `workflowState="InProgress"`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-TRANS-105`.
2 | Scroll to `CaseDetailsFooter`. Click **Withdraw**. The `WithdrawConfirmationDialog` opens. |  | `WithdrawConfirmationDialog` opens.
3 | Type a withdrawal reason: `LE Metropolitan Police Service withdrew COPO order — file closed.` Click **Confirm Withdraw**. |  | State pill reads `Withdrawn`; case becomes read-only.
4 | Inspect chrome + timeline. |  | Notes timeline carries a Withdrawal note row. Pass criteria: • State `Withdrawn` reached. • Case read-only. • Withdrawal note persisted.
UAT-UKCOPO-LRMS-106 · Fulfillment `InProgress` → `NoDataProvided` (No Accounts Found)
Case: UKCOPO-LRMS-TRANS-106 · Persona: RS · Stage: Fulfillment · InProgress → Fulfillment · NoDataProvided · Case shape: United Kingdom / International / Court Order · 1 Consumer identifier · synthesised, all identifiers checked as not-found
Capability validated: `useWorkflowActions.noAccountsFound()` flips state to `NoDataProvided` (terminal) without changing stage. Verifies the No-Accounts-Found path from `AccountIdentifiersSection`.
Preconditions: (1) Seed `UKCOPO-LRMS-TRANS-106` from `LNS-2025-555444` with `workflowStage="Fulfillment"`, `workflowState="InProgress"`, identifier check status `not-found` for all identifiers (mock `targetSelectors/checkAccounts/{caseId}` returns no matches).
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-TRANS-106`.
2 | Scroll to Section 4 — `Identifier & Data Services`. Verify the identifier check has run and the Status column reads `Not Found` for each identifier. |  | All identifiers marked `Not Found`.
3 | In the section header, click **No Accounts Found** (this CTA appears when all identifiers resolve to not-found — closest LRMS action to "abort because no data exists"). |  | **No Accounts Found** action visible and enabled.
4 | Confirm in any modal that appears. |  | State pill flips to `No Data Provided`; case becomes read-only. Pass criteria: • State `NoDataProvided` reached. • Case read-only.
UAT-UKCOPO-LRMS-107 · Fulfillment `InProgress` → `PublishInProgress` (submitFulfillment)
Case: UKCOPO-LRMS-TRANS-107 · Persona: RS · Stage: Fulfillment · InProgress → Publish · PublishInProgress · Case shape: United Kingdom / International / Court Order · 1 Consumer identifier with at least 1 service+category · synthesised
Capability validated: `submitFulfillment` + `patchCaseDetails` in `CaseDetailsComponent.tsx:780-830` advances stage Fulfillment→Publish and state→`PublishInProgress`. Verifies the `canSubmitFulfillment` gate (`fulfillmentIdentifierCount > 0 AND fulfillmentServiceCount > 0 AND etag present`).
Preconditions: (1) Seed `UKCOPO-LRMS-TRANS-107` from `LNS-2025-555444` with `workflowStage="Fulfillment"`, `workflowState="InProgress"`, fulfillment plan saved (1 identifier × Outlook × Basic Subscriber Info, date range Jan 1 – Apr 22, 2026).
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-TRANS-107`.
2 | Scroll to `CaseDetailsFooter`. Hover over **Submit Fulfillment** — verify the tooltip is empty (no unmet gates). |  | **Submit Fulfillment** enabled.
3 | Click **Submit Fulfillment**. `FulfillmentSummaryDialog` opens. Click **Submit** in the dialog. |  | Dialog opens with plan summary; submit fires `submitFulfillment` mutation followed by `patchCaseDetails(workflowState=PublishInProgress)`.
4 | Wait for the route to swap. |  | Route still `/cases/UKCOPO-LRMS-TRANS-107` but page now renders `CollectionPrepDeliveryPage`; sidebar active marker → "Collection, Prep & Delivery"; state pill reads `Publish In Progress`. Pass criteria: • Stage Fulfillment → Publish. • State `PublishInProgress`. • Collection page renders.
UAT-UKCOPO-LRMS-108 · `PublishInProgress` → `PartiallyPublished` (server-driven)
Case: UKCOPO-LRMS-TRANS-108 · Persona: RS · Stage: Publish · PublishInProgress → Publish · PartiallyPublished · Case shape: United Kingdom / International / Court Order · 2+ services or categories · synthesised
Capability validated: Server-driven progress flips state to `PartiallyPublished` when some but not all categories complete publish. Verifies the polling/refetch path in `useCollectionPolling`.
Preconditions: (1) Seed `UKCOPO-LRMS-TRANS-108` from `LNS-2025-555444` with `workflowStage="Publish"`, `workflowState="PublishInProgress"`, two services configured (Outlook, OneDrive), mock collection results show Outlook complete + OneDrive in progress.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-TRANS-108`. `CollectionPrepDeliveryPage` mounts.
2 | Click **Check Job Status** in `CollectionPageHeader`. The view refetches. |  | Refetch triggers.
3 | After ~5s of `useCollectionPolling`, inspect the `CaseInfoBar` state pill. |  | State pill flips from `Publish In Progress` to `Partially Published`; `FulfillmentPipelineCard` Prepare column reads `1/2`. Pass criteria: • State `PartiallyPublished` reflects server state. • (If the server-driven write is not modelled in the current mock, log N/A.)
UAT-UKCOPO-LRMS-109 · `PublishInProgress` → `DeliveryInProgress` (submitToDelivery)
Case: UKCOPO-LRMS-TRANS-109 · Persona: RS · Stage: Publish · PublishInProgress → Publish · DeliveryInProgress · Case shape: United Kingdom / International / Court Order · 1 service/category with `publishJobId` + `deliveryJobId` present · synthesised
Capability validated: `useSubmitToDeliveryMutation` (`collectionApi`) POST `cases/delivery/submit` flips state to `DeliveryInProgress` when a category's Deliver action is fired and the per-row deliveryJobId is present.
Preconditions: (1) Seed `UKCOPO-LRMS-TRANS-109` at `workflowStage="Publish"`, `workflowState="PublishInProgress"`, all prepare jobs complete.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-TRANS-109`. `CollectionPrepDeliveryPage` mounts.
2 | Scroll to `FulfillmentTrackerSection`. Click the identifier row to expand. Click the **Deliver** action on a category row whose Phase Status reads `Ready to Deliver`. |  | Deliver fires `submitToDelivery`; state pill flips to `Delivery In Progress`; `FulfillmentPipelineCard` Delivery column counter increments. Pass criteria: • State `DeliveryInProgress` reached.
UAT-UKCOPO-LRMS-110 · `DeliveryInProgress` → `DeliveryComplete` (server-driven)
Case: UKCOPO-LRMS-TRANS-110 · Persona: RS · Stage: Publish · DeliveryInProgress → Publish · DeliveryComplete · Case shape: United Kingdom / International / Court Order · all categories delivered · synthesised
Capability validated: Server-driven delivery completion flips state to `DeliveryComplete` (terminal, in `END_STATES` per `workflow-rules.constants.ts:3-22`).
Preconditions: (1) Seed `UKCOPO-LRMS-TRANS-110` at `workflowStage="Publish"`, `workflowState="DeliveryInProgress"`, mock returns all delivery jobs complete on next poll.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-TRANS-110`.
2 | Click **Check Job Status**. Wait ~5s. |  | State pill flips to `Delivery Complete`; case becomes read-only. Pass criteria: • State `DeliveryComplete` reached; case read-only.
UAT-UKCOPO-LRMS-111 · `PublishInProgress` → `Resolved` (ResolveCaseDialog · default)
Case: UKCOPO-LRMS-TRANS-111 · Persona: RS · Stage: Publish · PublishInProgress → Publish · Resolved · Case shape: United Kingdom / International / Court Order · synthesised, mid-publish
Capability validated: `ResolveCaseDialog` POST `cases/{caseId}/resolve` with `resolutionStatus: Resolved` (the default selection). Verifies the canonical happy-path resolution.
Preconditions: (1) Seed `UKCOPO-LRMS-TRANS-111` at `workflowStage="Publish"`, `workflowState="PublishInProgress"`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-TRANS-111`.
2 | In `CollectionPageHeader`, click **Resolve Case**. `ResolveCaseDialog` opens. |  | Dialog opens.
3 | Verify the `Resolution Status` dropdown defaults to `Resolved`. |  | Default `Resolved`.
4 | Type a note. Click **Resolve Case** primary button. |  | Success toast `"Case Resolved"`; dialog closes; state pill `Resolved`; case read-only.
UAT-UKCOPO-LRMS-112 · `PublishInProgress` → `NoDataFound` (ResolveCaseDialog)
Case: UKCOPO-LRMS-TRANS-112 · Persona: RS · Stage: Publish · PublishInProgress → Publish · NoDataFound · Case shape: United Kingdom / International / Court Order · synthesised
Capability validated: `ResolveCaseDialog` with `resolutionStatus: NoDataFound` from the `TERMINAL_WORKFLOW_STATES` picker.
Preconditions: (1) Seed `UKCOPO-LRMS-TRANS-112` at `workflowState="PublishInProgress"`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-TRANS-112`.
2 | Click **Resolve Case** in header. In `ResolveCaseDialog`, change `Resolution Status` dropdown to `No Data Found`. Add note. Click **Resolve Case**. |  | State pill `No Data Found`; case read-only.
UAT-UKCOPO-LRMS-113 · `PublishInProgress` → `Cancelled` (ResolveCaseDialog)
Case: UKCOPO-LRMS-TRANS-113 · Persona: RS · Stage: Publish · PublishInProgress → Publish · Cancelled
Capability validated: ResolveCaseDialog with `resolutionStatus: Cancelled`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case → **Resolve Case** → select `Cancelled` → note → submit.
UAT-UKCOPO-LRMS-114 · `PublishInProgress` → `Invalid` (ResolveCaseDialog)
Case: UKCOPO-LRMS-TRANS-114 · Persona: RS · Stage: Publish · PublishInProgress → Publish · Invalid
Capability validated: ResolveCaseDialog with `resolutionStatus: Invalid`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case → **Resolve Case** → select `Invalid` → note → submit.
UAT-UKCOPO-LRMS-115 · `PublishInProgress` → `Withdrawn` (ResolveCaseDialog)
Case: UKCOPO-LRMS-TRANS-115 · Persona: RS · Stage: Publish · PublishInProgress → Publish · Withdrawn
Capability validated: ResolveCaseDialog with `resolutionStatus: Withdrawn`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case → **Resolve Case** → select `Withdrawn` → note → submit.
UAT-UKCOPO-LRMS-116 · `PublishInProgress` → `Rejected` (ResolveCaseDialog)
Case: UKCOPO-LRMS-TRANS-116 · Persona: RS · Stage: Publish · PublishInProgress → Publish · Rejected
Capability validated: ResolveCaseDialog with `resolutionStatus: Rejected`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case → **Resolve Case** → select `Rejected` → note → submit.
UAT-UKCOPO-LRMS-117 · `PublishInProgress` → `NoDataProvided` (ResolveCaseDialog)
Case: UKCOPO-LRMS-TRANS-117 · Persona: RS · Stage: Publish · PublishInProgress → Publish · NoDataProvided
Capability validated: ResolveCaseDialog with `resolutionStatus: NoDataProvided` chosen at publish stage (distinct from the no-accounts-found path at fulfillment stage in UAT-UKCOPO-LRMS-106).
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case → **Resolve Case** → select `No Data Provided` → note → submit.
UAT-UKCOPO-LRMS-118 · `*` → `WaitingOnTriage` (returnToTriage from Fulfillment)
Case: UKCOPO-LRMS-TRANS-118 · Persona: RS · Stage: Fulfillment · InProgress → Triage · WaitingOnTriage · Case shape: United Kingdom / International / Court Order · synthesised, in Fulfillment
Capability validated: `useWorkflowActions.returnToTriage()` clears `assigneeName` and sets stage back to Triage, state back to `WaitingOnTriage`. Verifies `canReturnToTriage` gate (`!isTriageStage AND !isReadOnly`).
Preconditions: (1) Seed `UKCOPO-LRMS-TRANS-118` at `workflowStage="Fulfillment"`, `workflowState="InProgress"`, `assigneeName=<RS user>`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-TRANS-118`.
2 | Scroll to `CaseDetailsFooter`. Click **Return to Triage**. `ReturnToTriageDialog` opens. |  | Dialog opens.
3 | Type a note: `RS returning to Triage — UK regulatory review needs re-check.` Click **Confirm**. |  | `useWorkflowActions.returnToTriage()` fires.
4 | Inspect chrome. |  | State pill `Waiting on Triage`; sidebar Triage active again; `CaseInfoBar` Assignee chip reads `Unassigned` (assignee cleared); `TriageStepsBanner` reverts to `Triage Quick Steps`. Pass criteria: • State `WaitingOnTriage`. • Stage `Triage`. • Assignee cleared.
UAT-UKCOPO-LRMS-200 · CountrySelector behaviour for "United Kingdom" + persistence
Case: UKCOPO-LRMS-ALIAS-SYNTH · Persona: TS · Stage: Intake (pre-creation) · Case shape: pre-case state — only the CountrySelector + RequestWizard local state
Capability validated: `CountrySelector.tsx` (line 24–481) renders the UK tile correctly (id=54, code="UK", name="United Kingdom", isDSACountry=false) and emits the full `Country` object via `onCountrySelect`. Verifies the wizard branch (`country.code !== 'USA'` ⇒ InternationalWizard) and the UK label appears in the wizard header. **Note**: The InternationalWizard itself is currently a stub ("Under Development" Alert at `InternationalWizard.tsx`), so end-to-end submission via the wizard is N/A — this test only validates the selector + persistence into local state.
Preconditions: (1) Default queue. (2) Open the Request Creation wizard at the entry route (typically `/cases/new` or the "+ New Request" CTA in the queue toolbar).
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | From the Case Queue, click the **+ New Request** button. `RequestWizard` mounts. The first surface rendered is `CountrySelector` (because `country` state is null).
2 | In the search box at the top of `CountrySelector`, type `United Kingdom`. The grid filters to one tile. |  | Grid filters to "United Kingdom" tile only.
3 | Verify the tile shows: name `United Kingdom`, code badge `UK`, no DSA chip (since `isDSACountry=false`). |  | Tile copy: `United Kingdom` / `UK` / no DSA chip.
4 | Click the tile. `onCountrySelect(country)` fires with the full `Country` object `{ id: 54, name: 'United Kingdom', code: 'UK', isDSACountry: false, manualDelivery: false, countryContactReview: false }`. |  | `onCountrySelect` fires with the documented Country object.
5 | The wizard advances. Verify the header now reads `Country: United Kingdom`. |  | Header `Country: United Kingdom`.
6 | Verify the InternationalWizard mounts (because `country.code !== 'USA'`). The wizard body renders the "Under Development" Alert (current stub state — N/A for end-to-end completion). |  | InternationalWizard mounts with stub Alert (current build state — log as N/A for downstream wizard completion).
7 | Click the **Change Country** ghost button in the header. The wizard returns to `CountrySelector`. |  | Change Country returns to CountrySelector. Pass criteria: • UK tile renders + selects correctly. • Wizard branches to InternationalWizard. • Change Country resets selection. • (Downstream end-to-end submission via wizard logged N/A.)
UAT-UKCOPO-LRMS-201 · `UK_ALIASES` normalization
Case: UKCOPO-LRMS-ALIAS-SYNTH · Persona: TS · Stage: Triage (Section 2 — Legal & Compliance) · Case shape: synthesised case where `country` is iterated through each alias
Capability validated: `isUnitedKingdom(country)` (`countryUtils.ts`) tests membership in `UK_ALIASES = Set(['gb', 'uk', 'gbr', 'united kingdom', 'great britain'])` after lowercase+trim. Verifies all five aliases resolve to the UK-specific code paths (triage gate + EU27 DSA harms gate).
Preconditions: (1) Seed five synthesised cases `UKCOPO-LRMS-ALIAS-GB`, `UKCOPO-LRMS-ALIAS-UK`, `UKCOPO-LRMS-ALIAS-GBR`, `UKCOPO-LRMS-ALIAS-UKLOW`, `UKCOPO-LRMS-ALIAS-GREATBRITAIN` cloned from `LNS-2025-555444` with `country` overridden to `gb`, `uk`, `gbr`, `united kingdom`, `Great Britain` respectively. All otherwise at `Triage · InProgress` with assignee + priority + nature-of-crime set.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | For each of the five synthesised cases, navigate to `/cases/{caseId}`.
2 | Scroll to Section 2 — `Legal & Compliance`. Expand the group + `RegulatoryComplianceSection` accordion.
3 | Without changing `regulatoryCompliance.reviewStatus` or `eu27DsaHarms`, scroll up to `TriageStepsBanner`. Hover **Complete Triage**.
4 | Verify the disabled tooltip lists `Regulatory compliance review status required` (or equivalent) — this proves `requiresRegulatoryReview` evaluated to true, i.e. `isUnitedKingdom(country)` returned true for the alias.
5 | Set `reviewStatus="Approved"` in `RegulatoryComplianceSection`.
6 | Re-hover **Complete Triage**. |  | Pass criteria: • All five aliases trigger the UK gate. • Setting `reviewStatus` clears the gate.
UAT-UKCOPO-LRMS-202 · Regulatory Compliance card under UK — `regulationType`, `applicableLaws`, `reviewStatus`, `reviewedBy`, `reviewDate`
Case: UKCOPO-LRMS-EU27-SYNTH · Persona: TS · Stage: Triage · InProgress · Case shape: United Kingdom / International / Court Order · synthesised
Capability validated: `RegulatoryComplianceSection.tsx` correctly captures all `RegulatoryComplianceDetails` fields (`src/api/types.ts` lines 79-90) under a UK country. Verifies the dropdown options match the `RegulationType` enum (`DSA ¦ GDPR ¦ MLAT ¦ CLOUD Act ¦ Other`) and `RegulatoryReviewStatus` (`Pending ¦ Under Review ¦ Approved ¦ Non-Compliant`).
Preconditions: (1) Seed `UKCOPO-LRMS-EU27-SYNTH` from `LNS-2025-555444` with `country="United Kingdom"`, all other regulatory fields blank.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-EU27-SYNTH`. Case Details mounts.
2 | Scroll to Section 2 — `Legal & Compliance`. Expand the group. Scroll past the two-column grid to the full-width `RegulatoryComplianceSection` accordion. Click its header.
3 | Verify the panel renders the following fields (per spec): |  | All fields render with the expected enum options.
4 | Wait for autosave (`CaseInfoBar` "Saving…" → "Last saved …"). |  | Autosave persists.
5 | Refresh the browser. Re-open the case. Re-expand Section 2 + `RegulatoryComplianceSection`. |  | All field values survive refresh (persisted via PATCH `cases/{id}`). Pass criteria: • All five fields capture + persist. • Enum option lists match `domain.constants.ts`.
UAT-UKCOPO-LRMS-203 · EU27 DSA harms field — UK suppression behaviour
Case: UKCOPO-LRMS-EU27-SYNTH · Persona: TS · Stage: Triage · InProgress · Case shape: United Kingdom / International / Court Order · synthesised, then country flipped
Capability validated: `RegulatoryComplianceSection.tsx` only renders the EU27 DSA Harms Combobox when `isUnitedKingdom(country)` is true — but the Combobox is rendered DISABLED with placeholder `"Applicable to UK cases only"` when `!isUK`, and ENABLED with placeholder `"Select DSA harms"` when `isUK`. Verifies the auto-clear `useEffect([isUK])` that resets `eu27DsaHarms = []` on country change. (Note: per discovery, UK is treated as the only enabling country here — EU27 members do NOT enable this Combobox, contrary to first intuition; this is the documented branching at `RegulatoryComplianceSection.tsx`.)
Preconditions: (1) Seed `UKCOPO-LRMS-EU27-SYNTH` from `LNS-2025-555444` with `country="United Kingdom"`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-EU27-SYNTH`. Expand Section 2 → `RegulatoryComplianceSection`.
2 | Verify the `EU 27 DSA harms` Combobox is **enabled** and its placeholder reads `Select DSA harms`. Open it and select two harms (e.g. `Illegal content`, `Disinformation`). The chips persist. |  | Combobox enabled with `Select DSA harms` placeholder; two harms selectable.
3 | Save (wait for autosave). Verify in `CaseInfoBar` the "Last saved" timestamp updates. |  | Save persists the harms.
4 | Now flip the country: scroll up to `LegalClassificationSection`, change `Country` dropdown from `United Kingdom` to (e.g.) `Germany`. |  | Country change to Germany.
5 | Scroll back to `RegulatoryComplianceSection`. Inspect the `EU 27 DSA harms` Combobox. |  | Combobox is now DISABLED with placeholder `Applicable to UK cases only`; previously-selected harms have been auto-cleared by the `useEffect([isUK])` hook (eu27DsaHarms reset to `[]`).
6 | Flip the country back to `United Kingdom`. Inspect the Combobox. |  | Combobox re-enabled with `Select DSA harms`; chips are empty (the previous values are not restored). Pass criteria: • UK enables Combobox. • Non-UK disables Combobox with the correct placeholder. • Country flip auto-clears the harms array.
UAT-UKCOPO-LRMS-204 · Shield Law confirmation — UK applicability (off)
Case: UKCOPO-LRMS-EU27-SYNTH · Persona: TS · Stage: Triage · InProgress · Case shape: United Kingdom / International / Court Order · synthesised
Capability validated: `LegalComplianceCard.tsx` Shield Law toggle is enabled ONLY when `isUnitedStates(country)` returns true. UK does NOT enable Shield Law. Verifies the symmetric US-gate in `countryUtils.ts`.
Preconditions: (1) Seed `UKCOPO-LRMS-EU27-SYNTH` with `country="United Kingdom"`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-EU27-SYNTH`. Expand Section 2.
2 | Locate `LegalComplianceCard` in the right column of the two-column grid.
3 | Inspect the Shield Law row. |  | Shield Law toggle is either NOT RENDERED or rendered DISABLED with a tooltip indicating "US-only". The MLAT toggle on the same card IS visible and toggleable regardless of country. Pass criteria: • Shield Law gated off for UK. • MLAT toggle remains independent.
UAT-UKCOPO-LRMS-205 · DocumentPanel supporting affidavit attachment + verification
Case: LNS-2025-555444 · Persona: TS · Stage: Triage · InProgress · Case shape: United Kingdom / International / Court Order · synthesised with affidavit attachment
Capability validated: `DocumentPanel.tsx` is the canonical surface for affidavit / supporting-document upload during Triage. Verifies the `getAttachment`/`onVerificationPersist` round-trip (`AttachmentDocumentStatus.Valid ¦ Rejected ¦ Unverified`) and the optimistic UI. Note: the `DOCUMENT_VERIFICATION_GATES_TRIAGE = false` flag at `useWorkflowTransitions.ts:84-97` means unverified documents do NOT block triage today.
Preconditions: (1) UK seed case `LNS-2025-555444` open at Triage·InProgress with at least one mock attachment in `caseData.attachments` (typed `Affidavit` or `Court Order`).
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/LNS-2025-555444`.
2 | In the `CaseInfoBar` at the top, find the Documents toggle button (DocumentRegular icon) on the right side. The button shows an attachmentCount badge. Click it (or press Alt+D). |  | Documents button visible with badge.
3 | The `DocumentPanel` slides in from the right. |  | Panel slides in.
4 | At the top of the panel, find the combobox listing all attachments. Pick the first attachment. |  | Combobox + chip row populated.
5 | The viewer (PDF embed / image / iframe) renders the document. |  | Viewer renders.
6 | Below the viewer, find the `Document Type`, `Document Status`, `Document ID`, `Document Name`, `Start Date`, `Expiration Date` fields. Verify they are populated from the seed. |  | Validation grid populated.
7 | At the bottom of the panel, locate the verification banner. Click **Verify**. |  | Verify action enabled.
8 | Verify the optimistic update: the panel immediately shows a Verified card with the current user's name + timestamp. |  | Optimistic verified card appears.
9 | After ~1s, the persist completes (no error MessageBar appears). |  | No persistError MessageBar.
10 | Click **Undo**. The verification reverts to `Unverified`. |  | Undo reverts to Unverified.
11 | Type a rejection reason into the Notes textarea: `Affidavit signature illegible.` Click **Reject**. |  | Reject action with reason fires.
12 | The panel shows a Rejected card with the reason. |  | Rejected card visible.
13 | Press Esc. The panel closes. |  | Esc closes the panel. Pass criteria: • Verify / Undo / Reject round-trip works. • Notes/reason persist. • Esc closes panel.
UAT-UKCOPO-LRMS-206 · Audit-logging spec coverage — every stage transition leaves a note row
Case: LNS-2025-555444 · Persona: TS (Triage stages) + RS (Fulfillment / Publish / Delivery / Resolved stages) · Stage: Triage · WaitingOnTriage → Publish · Resolved (full walk) · Case shape: United Kingdom / International / Court Order · synthesised
Capability validated: Per the spec (`C:\R\LENS-LRMS\Specs\case-stage-state-audit-logging.md`), every stage transition (Intake > Triage > Fulfillment > Publish > Delivery > Resolved) must be audit-logged. Verifies (or documents the gap in) the WebClient's audit surface. Per discovery, the WebClient does NOT auto-emit audit log entries today — this test treats `OperationalReviewCard` (Section 6) as the proxy timeline and explicitly records the structural gap.
Preconditions: (1) Seed `UKCOPO-LRMS-AUDIT-SYNTH` from `LNS-2025-555444` at `Triage · WaitingOnTriage`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases/UKCOPO-LRMS-AUDIT-SYNTH`.
2 | Walk the case end-to-end following Parts A–G of UAT-UKCOPO-LRMS-001 (Triage assign → triageComplete → Fulfillment plan save → submitFulfillment → Publish prepare → deliver → Resolve).
3 | At each stage transition, open Section 6 (Operational Case Review) → `All` tab. Record whether an auto-emitted note row appears for the transition.
4 | Specifically check for these expected event types per spec: `TriageStarted`, `TriageCompleted`, `FulfillmentPlanSaved`, `FulfillmentSubmitted`, `CollectionStarted`, `PrepareCompleted`, `DeliveryCompleted`, `CaseResolved`. |  | Each named event type is either visible OR logged as a structural FAIL against the spec file.
5 | Also verify each metric per spec: `AcknowledgementTotalTime`, `TriageCompleteTotalTime`, `CollectionSuccessTotalTime`, `PrepareSuccessTotalTime`, `DeliverSuccessTotalTime`, `CaseResolvedTotalTime` — note that these are timing metrics, not note rows, and may not be UI-visible. |  | Timing metrics are likely server-side and not in the WebClient — log N/A and reference the spec. Pass criteria: • If the WebClient auto-emits stage transitions: each named event is present. • If the WebClient does NOT auto-emit (current state): the structural gap is documented per spec, and at minimum the user-written notes captured during the walk are present (e.g. recommendation, withdrawal, resolve notes).
UAT-UKCOPO-LRMS-SMOKE-A · Open UK seed case, verify UK-specific chrome renders
Case: LNS-2025-555444 · Persona: TS · Stage: Triage · Waiting on Triage (or whatever the seed lands at)
Capability validated: The UK seed mock case loads without error and the UK-specific chrome (`country=United Kingdom` in Section 2, `regulatoryCompliance.regulationType="CLOUD Act"` in `RegulatoryComplianceSection`, Westminster Magistrates' Court in Section 3) is visible.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Navigate to `/cases`. Click row `LNS-2025-555444`.
2 | Expand Section 2 → verify `Country = United Kingdom`.
3 | Expand Section 2 → `RegulatoryComplianceSection` → verify `Regulation Type = CLOUD Act`.
4 | Expand Section 3 → `AuthorizationsSection` → verify `Issuing Authority = Westminster Magistrates' Court`.
UAT-UKCOPO-LRMS-SMOKE-B · Triage gate refuses to advance without regulatory review
Case: LNS-2025-555444 · Persona: TS · Stage: Triage · InProgress
Capability validated: `canCompleteTriage` blocks triageComplete when UK case has `regulatoryCompliance.reviewStatus` unset and `eu27DsaHarms = []`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case. Hover **Complete Triage**.
2 | Read the tooltip. |  | Tooltip lists `Regulatory compliance review status required` (or equivalent text from `useWorkflowTransitions.triageGateErrors`).
UAT-UKCOPO-LRMS-SMOKE-C · Fulfillment wizard Step 2 — bulk services + date range save
Case: LNS-2025-555444 · Persona: RS · Stage: Fulfillment · Wizard
Capability validated: Fulfillment wizard Step 2 in Bulk mode accepts a date range + service+category selection and saves without error.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case. Section 4 → footer **Open Fulfillment Wizard**.
2 | Step 1 → **Next**.
3 | Step 2 → set `DataCollectionPeriod` start `2026-01-01`, end `2026-04-22`. Tick Outlook + Basic Subscriber Info.
4 | **Next** → Step 3 → **Save**. |  | Save toast renders; return to `/cases/{id}`.
UAT-UKCOPO-LRMS-SMOKE-D · Submit Fulfillment → Publish landing page renders
Case: LNS-2025-555444 · Persona: RS · Stage: Fulfillment · InProgress → Publish · PublishInProgress
Capability validated: `submitFulfillment` transitions stage to Publish and the route renders `CollectionPrepDeliveryPage`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case. `BottomActionBar` → **Submit Fulfillment** → dialog **Submit**.
2 | Observe the route swap. |  | `CollectionPrepDeliveryPage` renders with `CollectionPageHeader` + `FulfillmentPipelineCard`.
UAT-UKCOPO-LRMS-SMOKE-E · Resolve Case dialog → Resolved terminal
Case: LNS-2025-555444 · Persona: RS · Stage: Publish · PublishInProgress → Publish · Resolved
Capability validated: `ResolveCaseDialog` with default `Resolved` selection transitions the case to terminal `Resolved` state.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case. `CollectionPageHeader` → **Resolve Case**.
2 | Default dropdown `Resolved`. Type note. **Resolve Case**. |  | Success toast; state pill `Resolved`; case read-only.