## Cover
Document | UAT-UKCOPO — UK COPO request type test plan
Source | docs/uat/UAT-UKCOPO.md (full markdown narrative, decision trees & cross-refs)
Companion | docs/uat/UAT-UKCOPO-DecisionTrees.docx (decision tree narrative — Family 3 reference)
Generated | 2026-06-01 18:42:03
Total tests | 82
Family 1 | 70 per-service end-to-end tests (001-070)
Family 2 | Automated vs manual verification matrix (single matrix table in source markdown §5.3)
Family 3 | 12 authorization-status update tests (100-114) — see Word companion for decision trees
Smoke tests | 0 (SMOKE-A through SMOKE-G)
Sheet layout | Each test case is a stacked block: 3 metadata rows + 1 column-header row + N step rows + 1 blank separator.
Pass/Fail enum | Pass · Fail · Blocked · Not Run (data validation on the Pass/Fail? column).
Tester rows | Empty — tester to fill in.
Step rows | Pre-populated with the action ("Steps To Perform Test") and the matching "Expected Results" — both pulled verbatim from the source markdown.

## Test Cases
UAT-UKCOPO-001 · UK COPO · MSA · Subscriber Data · Basic Subscriber Data (automated)
Case: LNS-2026-00160 · Persona: TS (primary), RS (secondary) · Stage: Triage → Fulfillment → Submission → Collection → Packaging → Delivery · Case shape: GB / National England and Wales / COPO Order · 1 Consumer email identifier `subject-uk@outlook.com` · CSE-exempt overlay · attorneyEscalation Pending (ATT-001)
Capability validated: MSA `genericAttributes` lands the automated subscriber-data path; CollectionTracker auto-advances; Package + Deliver fire without manual entry.
Preconditions: (1) Default queue. (2) Acknowledge the attorney escalation as ATT-001 before walking the pipeline (CSE-exempt cases route through `AttorneyReviewPanel` first).
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case from the queue.
2 | In Triage, confirm the LE-external → LENS service-name resolver maps `Microsoft Account Profile` to `msaProfile` on first mount. |  | Resolver chip shows "Microsoft Account Profile → msaProfile" with a green Resolved badge.
3 | Enable `msaProfile` on the identifier; under Subscriber Data, leave only `Basic Subscriber Data` checked and disable all other items.
4 | Push to Fulfillment Wizard. In Step 2, confirm `Basic Subscriber Data` is marked **Automated**. |  | Item carries an "Automated" pill in the PlanReviewTable.
5 | Submit and open CollectionTracker. Observe job auto-advance through `Started → Complete`. |  | Pipeline status matrix flips green within the simulated tick; no `ManualCollectionForm` mounts.
6 | Package. Confirm the deliverable manifest lists MSA subscriber-data attributes per the `info` field (`Name (Reg); CID (hex); PUID; Address; Phone Number; Creation Date; …`). |  | Manifest preview lists the verbatim `info` attribute string.
7 | Deliver. Confirm Delivery succeeds and the audit thread records `JobCompleted → DeliveryAcknowledged`. |  | Audit thread shows `JobCompleted` (LENS automation) and `DeliveryAcknowledged` (RS).
UAT-UKCOPO-002 · UK COPO · MSA · Subscriber Data · Date of Birth (automated)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: MSA `dateOfBirth` automated path produces a single-attribute deliverable.
Preconditions: (1) Default queue. Acknowledge attorney escalation first.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case and push to Fulfillment Wizard.
2 | In Step 2, enable `msaProfile` and under Subscriber Data leave only `Date of Birth` checked. |  | `Date of Birth` carries an "Automated" pill.
3 | Submit and walk CollectionTracker → Package → Deliver. |  | CollectionTracker auto-advances; manifest contains only "Date of Birth"; Delivery succeeds.
UAT-UKCOPO-003 · UK COPO · MSA · Subscriber Data · Gender (automated)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: MSA `gender` automated path.
Preconditions: (1) Default queue. Acknowledge attorney escalation first.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `msaProfile`, under Subscriber Data check only `Gender`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest contains only "Gender"; Delivery succeeds.
UAT-UKCOPO-004 · UK COPO · MSA · Subscriber Data · Device Info (automated)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: MSA `deviceInfo` automated path.
Preconditions: (1) Default queue. Acknowledge attorney escalation first.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `msaProfile`, under Subscriber Data check only `Device Info`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest contains "Device Info"; Delivery succeeds.
UAT-UKCOPO-005 · UK COPO · MSA · Subscriber Data · Basic Billing (manual)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: MSA `basicBilling` routes to `ManualCollectionForm`; RS enters billing data and attaches evidence; status set by hand.
Preconditions: (1) Default queue. Acknowledge attorney escalation first.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `msaProfile`, under Subscriber Data check only `Basic Billing`. |  | "Manual" pill renders on Basic Billing in PlanReviewTable.
3 | Submit. In CollectionTracker, click the Basic Billing job row. |  | Job row does NOT auto-advance; status stays `Pending` until RS opens it.
4 | Confirm `ManualCollectionForm` opens. Enter Billing Address, Account Holder Name, Expiration Date, Payment Method Last 4. Attach a stub evidence file. |  | `ManualCollectionForm` renders with named fields matching the `info` string.
5 | Set status to `Complete`. Save. |  | Status flips to `Complete`; audit thread shows `ManualCollectionRecorded`.
6 | Package and Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-006 · UK COPO · MSA · Authentication Logs · Basic Authentication/IP (automated)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: MSA `authenticationLogs.genericAttributes` automated path; auth/IP history deliverable.
Preconditions: (1) Default queue. Acknowledge attorney escalation first.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `msaProfile`, under Authentication Logs check only `Basic Authentication/IP`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Auth Logs / IP History"; Delivery succeeds.
UAT-UKCOPO-007 · UK COPO · MSA · Traffic Data · 2FA / MFA / Proof (manual)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: MSA `trafficData.2FAMFAProof` manual path.
Preconditions: (1) Default queue. Acknowledge attorney escalation first.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `msaProfile`, under Traffic Data check only `2FA / MFA / Proof`. |  | "Manual" pill renders.
3 | Submit. Open the `2FA / MFA / Proof` job row in CollectionTracker. |  | Job row does not auto-advance.
4 | In `ManualCollectionForm`, enter MFA method details, proof timestamps, attach a stub evidence file. |  | `ManualCollectionForm` opens; RS-entered values persist on save.
5 | Set status `Complete`. Save.
6 | Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-008 · UK COPO · MSA · Traffic Data · Push Tokens (manual)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: MSA `pushTokens` manual path.
Preconditions: (1) Default queue. Acknowledge attorney escalation first.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `msaProfile`, under Traffic Data check only `Push Tokens`. |  | "Manual" pill renders.
3 | Submit. Open job row. Enter push token records and attach evidence in `ManualCollectionForm`. |  | `ManualCollectionForm` opens; manual entry persists.
4 | Set status `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-009 · UK COPO · MSA · Traffic Data · Detailed Billing (manual)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: MSA `detailedBilling` manual path.
Preconditions: (1) Default queue. Acknowledge attorney escalation first.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `msaProfile`, under Traffic Data check only `Detailed Billing`. |  | "Manual" pill renders.
3 | Submit, open the manual job, enter detailed billing rows, attach evidence. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-010 · UK COPO · MSA · Traffic Data · Reverse 2FA (manual)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: MSA `reverse2FA` manual path.
Preconditions: (1) Default queue. Acknowledge attorney escalation first.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `msaProfile`, under Traffic Data check only `Reverse 2FA`. |  | "Manual" pill renders.
3 | Submit, open job, manually enter reverse-lookup results, attach evidence. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-011 · UK COPO · MSA · Traffic Data · Reverse IP (manual)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: MSA `reverseIP` manual path.
Preconditions: (1) Default queue. Acknowledge attorney escalation first.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `msaProfile`, under Traffic Data check only `Reverse IP`. |  | "Manual" pill renders.
3 | Submit, open job, manually enter reverse-IP lookup results, attach evidence. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-012 · UK COPO · MSA · Content Data · Unified Audit Logs (manual)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: MSA `contentData.unifiedAuditLogs` manual path.
Preconditions: (1) Default queue. Acknowledge attorney escalation first.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `msaProfile`, under Content Data check only `Unified Audit Logs`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach UAL CSV/JSON exports. |  | Manual entry persists; file attachments saved.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-013 · UK COPO · Exchange Consumer · Traffic Data · Email Headers (Non-Content) (automated)
Case: LNS-2026-00170 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier · no escalation
Capability validated: ExchangeConsumer `emailHeadersNonContent` automated path on the clean rehearsal case.
Preconditions: (1) Default queue.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open `LNS-2026-00170` and push to Fulfillment.
2 | Confirm `Email` resolves to `exchangeConsumer`. Enable `exchangeConsumer`. |  | Resolver shows "Email → exchangeConsumer".
3 | Under Traffic Data check only `Email Headers (Non-Content)`. |  | "Automated" pill renders.
4 | Submit and walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Email Headers (Non-Content)"; Delivery succeeds.
UAT-UKCOPO-014 · UK COPO · Exchange Consumer · Content Data · Content Data (automated)
Case: LNS-2026-00170 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: ExchangeConsumer `contentData.genericAttributes` (Email Content) automated path.
Preconditions: (1) Default queue.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open `LNS-2026-00170`, push to Fulfillment.
2 | Enable `exchangeConsumer`, under Content Data check only `Content Data`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Email Content"; Delivery succeeds.
UAT-UKCOPO-015 · UK COPO · Exchange Consumer · Content Data · Email Headers (automated)
Case: LNS-2026-00170 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: ExchangeConsumer `emailHeaders` automated path.
Preconditions: (1) Default queue.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open `LNS-2026-00170`, push to Fulfillment.
2 | Enable `exchangeConsumer`, under Content Data check only `Email Headers`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Email Headers"; Delivery succeeds.
UAT-UKCOPO-016 · UK COPO · Exchange Consumer · Content Data · Email Contacts (automated)
Case: LNS-2026-00170 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: ExchangeConsumer `emailContacts` automated path.
Preconditions: (1) Default queue.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open `LNS-2026-00170`, push to Fulfillment.
2 | Enable `exchangeConsumer`, under Content Data check only `Email Contacts`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Email Contacts"; Delivery succeeds.
UAT-UKCOPO-017 · UK COPO · Exchange Consumer · Content Data · Email Calendar (automated)
Case: LNS-2026-00170 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: ExchangeConsumer `emailCalendar` automated path.
Preconditions: (1) Default queue.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open `LNS-2026-00170`, push to Fulfillment.
2 | Enable `exchangeConsumer`, under Content Data check only `Email Calendar`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Email Calendar"; Delivery succeeds.
UAT-UKCOPO-018 · UK COPO · Teams for Life · Content Data · Generic Content (automated)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier · CSE overlay
Capability validated: TeamsForLife `genericAttributesChats` automated path (Teams Chat Messaging deliverable).
Preconditions: (1) Default queue. Acknowledge attorney escalation first.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open `LNS-2026-00160`, push to Fulfillment.
2 | Confirm `Teams` resolves to `teamsForLife`. Enable it. |  | Resolver shows "Teams → teamsForLife".
3 | Under Content Data check only `Generic Content`. |  | "Automated" pill renders.
4 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Teams Chat Messaging"; Delivery succeeds.
UAT-UKCOPO-019 · UK COPO · Teams for Life · Content Data · Teams Live Intercept (manual)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: TeamsForLife `teamsLiveIntercept` manual path.
Preconditions: (1) Default queue. Acknowledge attorney escalation first.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `teamsForLife`, under Content Data check only `Teams Live Intercept`. |  | "Manual" pill renders.
3 | Submit, open job, manually configure intercept window + attach intercept evidence. |  | `ManualCollectionForm` opens; intercept config persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-020 · UK COPO · OneDrive for Consumer · Traffic Data · Generic Traffic Data (automated)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: OneDriveConsumer `trafficData.genericAttributes` (API Logs) automated path.
Preconditions: (1) Default queue. Acknowledge attorney escalation first.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Confirm `OneDrive` resolves to `oneDriveConsumer`. Enable it. |  | Resolver shows "OneDrive → oneDriveConsumer".
3 | Under Traffic Data check only `Generic Traffic Data`. |  | "Automated" pill renders.
4 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "API Logs"; Delivery succeeds.
UAT-UKCOPO-021 · UK COPO · OneDrive for Consumer · Content Data · Content Data (manual)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: OneDriveConsumer `contentData.genericAttributes` (OneDrive Content) manual path — content is always manual for OneDrive Consumer.
Preconditions: (1) Default queue. Acknowledge attorney escalation first.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `oneDriveConsumer`, under Content Data check only `Content Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach OneDrive content export. |  | `ManualCollectionForm` opens.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-022 · UK COPO · XBOX · Subscriber Data (manual)
Case: UKCOPO-XBOX-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier (XBOX gamertag pattern)
Capability validated: XBOX `subscriberData.genericAttributes` manual path on a synthesised UK COPO Consumer identifier that carries `XBOX/Minecraft` in `leExternalServices`.
Preconditions: (1) Seed `UKCOPO-XBOX-SYNTH` from `LNS-2026-00170` template; mutate `leExternalServices = ["Microsoft Account Profile","XBOX/Minecraft"]` and confirm resolver maps to `xbox`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the synthesised case, push to Fulfillment.
2 | Enable `xbox`, under Subscriber Data check only `Basic Subscriber Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually enter Xbox Gamertag, MSA, Account Created Date, Customer Name, Country, Contact Email; attach evidence. |  | `ManualCollectionForm` exposes XBOX-shaped fields.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-023 · UK COPO · XBOX · Authentication Logs (manual)
Case: UKCOPO-XBOX-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: XBOX `authenticationLogs.genericAttributes` manual path.
Preconditions: (1) `UKCOPO-XBOX-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `xbox`, under Authentication Logs check only `Basic Authentication/IP`. |  | "Manual" pill renders.
3 | Submit, open job, manually enter IP history rows + serial-number + gamertag pairing, attach evidence. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-024 · UK COPO · XBOX · Traffic Data · Strike Logs (manual)
Case: UKCOPO-XBOX-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: XBOX `strikeLogs` manual path.
Preconditions: (1) `UKCOPO-XBOX-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `xbox`, under Traffic Data check only `Strike Logs`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach strike-log export. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-025 · UK COPO · XBOX · Traffic Data · Purchase History (manual)
Case: UKCOPO-XBOX-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: XBOX `purchaseHistory` manual path.
Preconditions: (1) `UKCOPO-XBOX-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `xbox`, under Traffic Data check only `Purchase History`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach purchase-history export. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-026 · UK COPO · XBOX · Traffic Data · PrePaid Balance (manual)
Case: UKCOPO-XBOX-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: XBOX `prePaidBalance` manual path.
Preconditions: (1) `UKCOPO-XBOX-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `xbox`, under Traffic Data check only `PrePaid Balance`. |  | "Manual" pill renders.
3 | Submit, open job, manually enter prepaid balance + supporting evidence. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-027 · UK COPO · XBOX · Content Data (manual)
Case: UKCOPO-XBOX-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: XBOX `contentData.genericAttributes` (Profile Photo, Clubs, Contacts, Content, Video, Voice) manual path.
Preconditions: (1) `UKCOPO-XBOX-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `xbox`, under Content Data check only `Content Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach the six content categories listed in the `info` field. |  | `ManualCollectionForm` lists all six XBOX content categories.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-028 · UK COPO · Skype · Content Data (manual)
Case: UKCOPO-SKYPE-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: Skype `contentData.genericAttributes` (Contact List / Buddy List) manual path.
Preconditions: (1) Seed `UKCOPO-SKYPE-SYNTH` from `LNS-2026-00170` template; add `Skype` to `leExternalServices` (note: not in current resolver map — manually enable `skype` in Step 2).
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | In Step 2, manually enable `skype` (resolver will surface "wrong-account-type" if account check returns non-Skype — override).
3 | Under Content Data check only `Content Data`. |  | "Manual" pill renders.
4 | Submit, open job, manually attach Skype buddy list export. |  | Manual entry persists.
5 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-029 · UK COPO · Minecraft · Traffic Data · Generic Traffic Data (manual)
Case: UKCOPO-MINECRAFT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: Minecraft `trafficData.genericAttributes` (Purchase History) manual path.
Preconditions: (1) Seed `UKCOPO-MINECRAFT-SYNTH` from `LNS-2026-00170` template; mutate `leExternalServices` to include `XBOX/Minecraft` and force resolution to `minecraft` (override XBOX if both compete).
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `minecraft`, under Traffic Data check only `Generic Traffic Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach Minecraft purchase-history export. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-030 · UK COPO · Minecraft · Content Data (manual)
Case: UKCOPO-MINECRAFT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: Minecraft `contentData.genericAttributes` (Minecraft Content) manual path.
Preconditions: (1) `UKCOPO-MINECRAFT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `minecraft`, under Content Data check only `Content Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach Minecraft content export. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-031 · UK COPO · GroupMe · Content Data (manual)
Case: UKCOPO-GROUPME-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: GroupMe `contentData.genericAttributes` (Chat Content) manual path.
Preconditions: (1) Seed `UKCOPO-GROUPME-SYNTH` from `LNS-2026-00170` template; manually enable `groupMe` (no resolver mapping today).
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Manually enable `groupMe`, under Content Data check only `Content Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach GroupMe chat export. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-032 · UK COPO · CoPilot Consumer · Content Data (manual)
Case: UKCOPO-COPILOT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: CoPilotConsumer `contentData.genericAttributes` (Prompts & Responses) manual path.
Preconditions: (1) Seed `UKCOPO-COPILOT-SYNTH` from `LNS-2026-00170` template; manually enable `coPilotConsumer`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `coPilotConsumer`, under Content Data check only `Content Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach CoPilot prompts & responses export. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-033 · UK COPO · DevTunnels · Traffic Data · Generic Traffic Data (manual)
Case: UKCOPO-ANY-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: DevTunnels `trafficData.genericAttributes` (Device Info) manual path on an any-scope service.
Preconditions: (1) Seed `UKCOPO-ANY-SYNTH` from `LNS-2026-00170` template; manually enable `devTunnels`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `devTunnels`, under Traffic Data check only `Generic Traffic Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach DevTunnels device info export. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-034 · UK COPO · DevTunnels · Content Data (manual)
Case: UKCOPO-ANY-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: DevTunnels `contentData.genericAttributes` manual path.
Preconditions: (1) `UKCOPO-ANY-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `devTunnels`, under Content Data check only `Content Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach DevTunnels content export. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-035 · UK COPO · BitLocker · Content Data (manual)
Case: UKCOPO-ANY-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: BitLocker `contentData.genericAttributes` (BitLocker Key) manual path on an any-scope service.
Preconditions: (1) `UKCOPO-ANY-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `bitlocker`, under Content Data check only `Content Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach BitLocker recovery key + provenance. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-036 · UK COPO · Microsoft Ads · Content Data (manual)
Case: UKCOPO-ANY-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: Microsoft Ads `contentData.genericAttributes` (Domain Names; Keywords) manual path.
Preconditions: (1) `UKCOPO-ANY-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `microsoftAds`, under Content Data check only `Content Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach Ads domain/keyword export. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-037 · UK COPO · Bing Search · Content Data (manual)
Case: UKCOPO-ANY-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: Bing Search `contentData.genericAttributes` manual path.
Preconditions: (1) `UKCOPO-ANY-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `bingSearch`, under Content Data check only `Content Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach Bing query content export. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-038 · UK COPO · Microsoft Forms · Subscriber Data (manual)
Case: UKCOPO-ANY-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: Microsoft Forms `subscriberData.genericAttributes` (Associated Account Information) manual path.
Preconditions: (1) `UKCOPO-ANY-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `microsoftForms`, under Subscriber Data check only `Basic Subscriber Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach Forms-associated account info. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-039 · UK COPO · Production Letters · Affidavit (manual; auto-enabled for COPO)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: Production Letters `disclosureLetters.affidavit` auto-enables on UK COPO cases (`autoEnabledForCOPO: true`, `requestTypeScope: ["COPO Order"]`); manual upload via the manual collection form's notes attachment.
Preconditions: (1) Default queue. Acknowledge attorney escalation first.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open `LNS-2026-00160`, push to Fulfillment.
2 | In Step 2, confirm `productionLetters` is auto-enabled (visible without explicit toggle) and `Affidavit` is pre-checked under Disclosure Letters. |  | `productionLetters` rendered as pre-selected with an "Auto-enabled (COPO)" badge.
3 | Submit, open the Affidavit job row. |  | Affidavit row marked "Manual"; does not auto-advance.
4 | In `ManualCollectionForm`, attach a sworn statement / supporting affidavit file in the notes attachment slot. |  | Notes attachment slot accepts the file.
5 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed; Affidavit appears in the delivered manifest.
UAT-UKCOPO-040 · UK COPO · EntraID · Subscriber Data · Basic Subscriber Data (automated)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: EntraID `subscriberData.genericAttributes` automated path on an Enterprise UK COPO identifier.
Preconditions: (1) Seed `UKCOPO-ENT-SYNTH`; confirm `Microsoft Account Profile` resolves to `entraIDProfile` for Enterprise account-type.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case, push to Fulfillment.
2 | Enable `entraIDProfile`, under Subscriber Data check only `Basic Subscriber Data`. |  | Resolver shows "Microsoft Account Profile → entraIDProfile (Enterprise)".
3 | Submit, walk CollectionTracker → Package → Deliver. |  | "Automated" pill renders; manifest carries PUID/Organization Profile attributes; Delivery succeeds.
UAT-UKCOPO-041 · UK COPO · EntraID · Subscriber Data · Language (automated)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: EntraID `language` automated path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `entraIDProfile`, under Subscriber Data check only `Language`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Language"; Delivery succeeds.
UAT-UKCOPO-042 · UK COPO · EntraID · Subscriber Data · Date of Birth (automated)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: EntraID `dateOfBirth` automated path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `entraIDProfile`, under Subscriber Data check only `Date of Birth`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Date of Birth"; Delivery succeeds.
UAT-UKCOPO-043 · UK COPO · EntraID · Subscriber Data · Device Info (automated)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: EntraID `deviceInfo` automated path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `entraIDProfile`, under Subscriber Data check only `Device Info`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Device Info"; Delivery succeeds.
UAT-UKCOPO-044 · UK COPO · EntraID · Subscriber Data · Gender (automated)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: EntraID `gender` automated path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `entraIDProfile`, under Subscriber Data check only `Gender`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Gender"; Delivery succeeds.
UAT-UKCOPO-045 · UK COPO · EntraID · Subscriber Data · Basic Billing (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: EntraID `basicBilling` manual path (Subscriptions; Billing Address; Account Holder Name; Expiration Date; Payment Method Last 4).
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `entraIDProfile`, under Subscriber Data check only `Basic Billing`. |  | "Manual" pill renders.
3 | Submit, open job, manually enter subscription + billing rows, attach evidence. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-046 · UK COPO · EntraID · Authentication Logs · Basic Authentication/IP (automated)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: EntraID `authenticationLogs.genericAttributes` automated path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `entraIDProfile`, under Authentication Logs check only `Basic Authentication/IP`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Auth Logs / IP History"; Delivery succeeds.
UAT-UKCOPO-047 · UK COPO · EntraID · Traffic Data · List of Accounts (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: EntraID `listOfAccounts` (SMTP) manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `entraIDProfile`, under Traffic Data check only `List of Accounts`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach SMTP account list. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-048 · UK COPO · EntraID · Traffic Data · List of Domains (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: EntraID `listOfDomains` (SMTP) manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `entraIDProfile`, under Traffic Data check only `List of Domains`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach SMTP domain list. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-049 · UK COPO · EntraID · Traffic Data · Detailed Billing (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: EntraID `detailedBilling` manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `entraIDProfile`, under Traffic Data check only `Detailed Billing`. |  | "Manual" pill renders.
3 | Submit, open job, manually enter detailed billing rows. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-050 · UK COPO · EntraID · Traffic Data · Password Change History (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: EntraID `passwordChangeHistory` manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `entraIDProfile`, under Traffic Data check only `Password Change History`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach password-change history. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-051 · UK COPO · EntraID · Traffic Data · Advertising Information (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: EntraID `advertisingInformation` (Bing Ads) manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `entraIDProfile`, under Traffic Data check only `Advertising Information`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach Bing Ads info. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-052 · UK COPO · EntraID · Traffic Data · Reverse 2FA (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: EntraID `reverse2FA` manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `entraIDProfile`, under Traffic Data check only `Reverse 2FA`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach reverse 2FA lookup. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-053 · UK COPO · EntraID · Traffic Data · Reverse IP (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: EntraID `reverseIP` manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `entraIDProfile`, under Traffic Data check only `Reverse IP`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach reverse-IP lookup. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-054 · UK COPO · Exchange Enterprise · Traffic Data · Password Change History (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: ExchangeEnterprise `passwordChangeHistory` manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `exchangeEnterprise`, under Traffic Data check only `Password Change History`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach Exchange Enterprise password-change history. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-055 · UK COPO · Exchange Enterprise · Traffic Data · Email Headers (Non-Content) (automated)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: ExchangeEnterprise `emailHeadersNonContent` automated path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `exchangeEnterprise`, under Traffic Data check only `Email Headers (Non-Content)`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Email Headers (Non-Content)"; Delivery succeeds.
UAT-UKCOPO-056 · UK COPO · Exchange Enterprise · Content Data · Content Data (automated)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: ExchangeEnterprise `contentData.genericAttributes` (Email Content) automated path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `exchangeEnterprise`, under Content Data check only `Content Data`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Email Content"; Delivery succeeds.
UAT-UKCOPO-057 · UK COPO · Exchange Enterprise · Content Data · Email Headers (automated)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: ExchangeEnterprise `emailHeaders` (Email Full Headers) automated path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `exchangeEnterprise`, under Content Data check only `Email Headers`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Email Full Headers"; Delivery succeeds.
UAT-UKCOPO-058 · UK COPO · Exchange Enterprise · Content Data · Email Contacts (automated)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: ExchangeEnterprise `emailContacts` automated path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `exchangeEnterprise`, under Content Data check only `Email Contacts`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Email Contacts"; Delivery succeeds.
UAT-UKCOPO-059 · UK COPO · Exchange Enterprise · Content Data · Email Calendar (automated)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: ExchangeEnterprise `emailCalendar` automated path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `exchangeEnterprise`, under Content Data check only `Email Calendar`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Email Calendar"; Delivery succeeds.
UAT-UKCOPO-060 · UK COPO · Teams for Business · Traffic Data · 2FA / MFA / Proof (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: TeamsForBusiness `2FAMFAProof` manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `teamsForBusiness`, under Traffic Data check only `2FA / MFA / Proof`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach MFA proof. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-061 · UK COPO · Teams for Business · Content Data · Generic Content (automated)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: TeamsForBusiness `genericAttributesChats` (Teams Chat Messaging) automated path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `teamsForBusiness`, under Content Data check only `Generic Content`. |  | "Automated" pill renders.
3 | Submit, walk CollectionTracker → Package → Deliver. |  | Auto-advance; manifest carries "Teams Chat Messaging"; Delivery succeeds.
UAT-UKCOPO-062 · UK COPO · OneDrive for Business · Content Data · Content Data (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: OneDriveForBusiness `contentData.genericAttributes` (OneDrive Content) manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `oneDriveForBusiness`, under Content Data check only `Content Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach OneDrive content export. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-063 · UK COPO · SharePoint Online · Content Data · Content Data (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: SharePointOnline `contentData.genericAttributes` (SharePoint Content) manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded with `SharePoint` in `leExternalServices`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Confirm `SharePoint` resolves to `sharePointOnline`. Enable it. |  | Resolver shows "SharePoint → sharePointOnline".
3 | Under Content Data check only `Content Data`. |  | "Manual" pill renders.
4 | Submit, open job, manually attach SharePoint content export. |  | Manual entry persists.
5 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-064 · UK COPO · CoPilot Enterprise · Content Data (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: CoPilotEnterprise `contentData.genericAttributes` manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `coPilotEnterprise`, under Content Data check only `Content Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach CoPilot prompts/responses + Tenant ID. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-065 · UK COPO · Azure Storage · Traffic Data · Generic Traffic Data (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: Azure Storage `trafficData.genericAttributes` (ARM Logs; Netflow IP) manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `azureStorage`, under Traffic Data check only `Generic Traffic Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach ARM logs + Netflow IP exports. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-066 · UK COPO · Azure Storage · Content Data · Content Data (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: Azure Storage `contentData.genericAttributes` (Blobs; Sites; File Shares; Tables and Queues) manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `azureStorage`, under Content Data check only `Content Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach Azure Storage content export. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-067 · UK COPO · Azure Storage · Content Data · Unified Audit Logs (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: Azure Storage `unifiedAuditLogs` manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `azureStorage`, under Content Data check only `Unified Audit Logs`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach UAL export. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-068 · UK COPO · Azure VM Disks · Traffic Data · Generic Traffic Data (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: Azure VM Disks `trafficData.genericAttributes` (ARM Logs; Netflow IP; VIP History) manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `azureVMDisks`, under Traffic Data check only `Generic Traffic Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach VM Disks traffic export. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-069 · UK COPO · Azure VM Disks · Content Data · Content Data (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: Azure VM Disks `contentData.genericAttributes` (Azure VMs & Disks) manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `azureVMDisks`, under Content Data check only `Content Data`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach VM image / disk content export. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-070 · UK COPO · Azure VM Disks · Content Data · Unified Audit Logs (manual)
Case: UKCOPO-ENT-SYNTH · Persona: RS · Stage: Fulfillment → Delivery · Case shape: GB / National / COPO Order · 1 Enterprise identifier
Capability validated: Azure VM Disks `unifiedAuditLogs` manual path.
Preconditions: (1) `UKCOPO-ENT-SYNTH` seeded.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open, push to Fulfillment.
2 | Enable `azureVMDisks`, under Content Data check only `Unified Audit Logs`. |  | "Manual" pill renders.
3 | Submit, open job, manually attach UAL export. |  | Manual entry persists.
4 | Set `Complete`. Package + Deliver. |  | Package + Deliver succeed.
UAT-UKCOPO-100 · Case-level `authorizationDesiredStatus = "Active"` (no-op baseline)
Case: LNS-2026-00170 · Persona: RS · Stage: Fulfillment · Case shape: GB / National / COPO Order · 1 Consumer identifier · clean
Capability validated: Baseline state — no banner, no chip beyond `CaseSummaryCard` outline, no gates. Confirms the absence of UI chrome when the IA's stated status is the trivial baseline.
Preconditions: (1) Default queue. Seed `formData.authorizationDesiredStatus = "Active"` (already the default on the clean case).
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open `LNS-2026-00170`.
2 | Inspect the sticky case header, page-top alert zone, and CaseSummaryCard. |  | No AuthorizationStatusBanner; CaseSummaryCard shows an outline badge labelled "Active".
3 | Push through Fulfillment Wizard to Step 3 (Plan Review). |  | Submit-to-Delivery enabled; no tooltip gate.
4 | Inspect the AuthorizationStatusBanner mount point in Step 3. |  | No banner mounts at Step 3.
UAT-UKCOPO-101 · Case-level `authorizationDesiredStatus = "Approved"` (untyped seed)
Case: LNS-2026-00170 · Persona: RS · Stage: Fulfillment · Case shape: GB / National / COPO Order · 1 Consumer identifier · clean
Capability validated: Untyped seed value "Approved" is treated as the human-readable equivalent of "Active"; no banner mounts, no gates fire.
Preconditions: (1) Default queue. The seed value `"Approved"` is the default on `LNS-2026-00170`.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open `LNS-2026-00170`.
2 | Inspect the sticky case header and CaseSummaryCard. |  | No AuthorizationStatusBanner; CaseSummaryCard shows outline "Approved".
3 | Push to Fulfillment Wizard Step 3. |  | Submit-to-Delivery enabled; no tooltip gate.
4 | Open AuthoritySignalSimulator and confirm "Approved" is selectable as the IA Form 4 dropdown value. |  | Simulator confirms "Approved" maps to the typed "Active" branch (no terminal predicate fires).
UAT-UKCOPO-102 · Case-level `authorizationDesiredStatus = "Cancelled"` (scope=all, terminal)
Case: LNS-2026-00170 · Persona: RS · Stage: Fulfillment → Collection · Case shape: GB / National / COPO Order · 1 Consumer identifier · mid-workflow
Capability validated: Full case-wide cancellation via `applyAuthorizationStatusUpdate(scope.kind="all", status="Cancelled")` — mirrors onto every identifier's `authorizationDesiredTaskStatus`, locks Package + Deliver, and on Acknowledge cascades `taskStatus = "Cancelled"` to every identifier.
Preconditions: (1) Open `LNS-2026-00170` and push through Fulfillment Wizard to Step 3, but do NOT submit. Leave the case at "mid-workflow" with a single pending job seeded in CollectionTracker.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open `AuthoritySignalSimulator` and select IA Form 4 with status `Cancelled`, scope `all`.
2 | Fire the signal. Observe the page-top alert zone. |  | Red `AuthorizationStatusBanner` mounts with copy `**"LE Cancelled — cease execution on the entire case"**` + Acknowledge CTA.
3 | Inspect the `AuthorizationStatusBanner` copy and CTAs. |  | `CaseHeaderSummary CancellationBadge` (red) appears at top of sticky header.
4 | Hover Package and Deliver buttons in CollectionTracker. |  | Package and Deliver buttons disabled with tooltip `*"Action blocked — authorization cancelled."*` (`cancellationLocked === true`).
5 | Click the banner's primary "Acknowledge" CTA. |  | Acknowledge fires; `formData.authorizationStatusAcknowledgedAt`, `authorizationStatusAcknowledgedBy` set.
6 | Inspect each identifier's `taskStatus` after Acknowledge. |  | Every identifier's `taskStatus === "Cancelled"` (case-level wins per cascade rule).
7 | Inspect the audit thread. |  | Audit thread shows `AuthorizationStatusUpdated` (scope=all, status=Cancelled) followed by `AuthorizationStatusAcknowledged`. Pass criteria: • Banner renders with correct copy. • Package + Deliver gated by `cancellationLocked`. • Acknowledge cascade flips every identifier `taskStatus` to "Cancelled". • Audit thread carries both events in order.
UAT-UKCOPO-103 · Case-level `authorizationDesiredStatus = "Withdrawn"` (terminal)
Case: LNS-2026-00170 · Persona: RS · Stage: Collection · Case shape: GB / National / COPO Order · 1 Consumer identifier · two pending jobs + one delivered job seeded
Capability validated: IA withdrawal via `applyWithdrawal` — sets `authorizationDesiredStatus="Withdrawn"`, `caseStage="Withdrawn"`, appends `EpocWithdrawn` audit, starts 45-day retention clock, and freezes Delivery.
Preconditions: (1) Open `LNS-2026-00170` and seed CollectionTracker with two pending jobs (Started status) plus one already-delivered job (DeliveryAcknowledged).
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Fire IA Withdrawal via `AuthoritySignalSimulator` (or direct seed).
2 | Inspect the page-top alert zone for `WithdrawalBanner`. |  | Red `WithdrawalBanner` renders at top of stack with copy `**"IA Withdrew the order"**` + Acknowledge CTA.
3 | Inspect the sticky-header chip for the Retention chip. |  | Retention chip `**"Retention · 45-day clock from effective date"**` lights up in sticky header.
4 | Inspect each pending job row in CollectionTracker. |  | Both pre-pending jobs flipped to `Cancelled`.
5 | Inspect the already-delivered job row. |  | Delivered job untouched.
6 | Inspect the audit thread. |  | Audit thread shows `EpocWithdrawn` event with effective date; `startRetentionClock("Withdrawn")` recorded. Pass criteria: • `WithdrawalBanner` renders with correct copy. • Two pre-pending jobs flipped to Cancelled; already-delivered job untouched. • `caseStage === "Withdrawn"`, `isCaseWithdrawn === true`. • Retention clock started.
UAT-UKCOPO-104 · Case-level `authorizationDesiredStatus = "Suspended"` (non-terminal)
Case: LNS-2026-00170 · Persona: RS · Stage: Fulfillment · Case shape: GB / National / COPO Order · 1 Consumer identifier · mid-workflow
Capability validated: IA's pause signal — advisory only; banner mounts but no gates fire; `isAuthorizationStatusTerminal` returns false.
Preconditions: (1) Open `LNS-2026-00170` and push to Fulfillment Wizard Step 3.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Fire IA Form 4 with status `Suspended`, scope `all` via `AuthoritySignalSimulator`.
2 | Inspect the page-top alert zone. |  | Amber `AuthorizationStatusBanner` renders with copy `**"LE Suspended — pause execution"**` + Acknowledge CTA.
3 | Hover Package and Deliver buttons. |  | Package and Deliver remain enabled (no auto-fired gate; `cancellationLocked === false`).
4 | Inspect the audit thread. |  | Audit thread shows `AuthorizationStatusUpdated` (scope=all, status=Suspended).
UAT-UKCOPO-105 · Case-level `authorizationDesiredStatus = "Expired"` (time-driven)
Case: LNS-2026-00170 · Persona: RS · Stage: Collection · Case shape: GB / National / COPO Order · 1 Consumer identifier · `authorizationExpirationDate` forced into the past
Capability validated: Time-driven aging out of the authorization — the status flips from "Active" / "Approved" to "Expired" once `authorizationExpirationDate` is passed. Advisory only; no gates auto-fire.
Preconditions: (1) Open `LNS-2026-00170` and override `formData.authorizationExpirationDate` to a date earlier than today via direct seed mutation. Reload.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open the case after the seed mutation.
2 | Inspect the page-top alert zone and CaseSummaryCard. |  | Amber `AuthorizationStatusBanner` renders with copy referencing the expired `authorizationExpirationDate`.
3 | Hover Package and Deliver buttons. |  | Package and Deliver remain enabled (`isAuthorizationStatusTerminal` returns false; no auto-gate).
4 | Inspect the audit thread. |  | Audit thread shows `AuthorizationStatusUpdated` (scope=all, status=Expired, source=timeBased).
UAT-UKCOPO-106 · Case-level `authorizationDesiredStatus = "Rejected"` (untyped seed)
Case: LNS-2026-00170 · Persona: RS · Stage: Fulfillment · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: Out-of-union string value flows through (FormData field is typed `string`); no banner, no gates, raw label shown.
Preconditions: (1) Force `formData.authorizationDesiredStatus = "Rejected"` via direct seed mutation.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open `LNS-2026-00170`.
2 | Inspect the page-top alert zone and CaseSummaryCard. |  | No banner mounts (value not in terminal set); CaseSummaryCard renders raw string "Rejected" with neutral tint.
3 | Inspect Package and Deliver buttons in CollectionTracker. |  | Package and Deliver remain enabled.
4 | Inspect the audit thread. |  | Audit thread shows `AuthorizationStatusUpdated` (scope=all, status=Rejected) if simulator pushed it; otherwise no entry.
UAT-UKCOPO-110 · Task-level `authorizationDesiredTaskStatus = "Requested"` (baseline)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: PlanReviewTable's per-identifier "Authorization" column renders `Requested` as an informative (neutral) Fluent badge; column only shows on `requestType === "COPO Order"` (or eEvidence).
Preconditions: (1) Force the identifier's `authorizationDesiredTaskStatus = "Requested"` via direct seed mutation.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open `LNS-2026-00160` and push to Fulfillment Wizard Step 3.
2 | Inspect the PlanReviewTable's "Authorization" column. |  | Per-identifier chip renders with text `"Requested"` in informative (neutral) Fluent color.
3 | Confirm no banner mounts and no gates fire. |  | No AuthorizationStatusBanner; Submit-to-Delivery enabled.
UAT-UKCOPO-111 · Task-level `authorizationDesiredTaskStatus = "Active"` (baseline)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: PlanReviewTable's "Authorization" column renders `Active` as a brand-color Fluent badge; no banner, no gates.
Preconditions: (1) Force the identifier's `authorizationDesiredTaskStatus = "Active"` via direct seed mutation.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Open `LNS-2026-00160` and push to Fulfillment Wizard Step 3.
2 | Inspect the PlanReviewTable. |  | Per-identifier chip renders `"Active"` in brand Fluent color.
3 | Confirm no banner mounts. |  | No AuthorizationStatusBanner; Submit-to-Delivery enabled.
UAT-UKCOPO-112 · Task-level `authorizationDesiredTaskStatus = "Suspended"` (per-task warn)
Case: LNS-2026-00160 · Persona: RS · Stage: Fulfillment · Case shape: GB / National / COPO Order · 1 Consumer identifier
Capability validated: Per-task pause signal via `scope.kind="some"` — case-level field cleared, per-identifier warn chip displayed, no case-level banner.
Preconditions: (1) Open `LNS-2026-00160` and push to Fulfillment Wizard Step 3.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Fire IA Form 4 with status `Suspended`, scope `some` (target the single identifier) via `AuthoritySignalSimulator`.
2 | Inspect the page-top alert zone (case-level banner mount). |  | No case-level `AuthorizationStatusBanner` mounts (applyAuthorizationStatusUpdate clears the case-level field on scope=some).
3 | Inspect the PlanReviewTable. |  | Per-identifier chip renders `"Suspended"` in warning (amber) Fluent color.
4 | Confirm `formData.authorizationDesiredStatus` is cleared to `""`. |  | `formData.authorizationDesiredStatus === ""`; `authorizationStatusUpdatedAt/By` zeroed.
5 | Inspect the audit thread. |  | Audit thread shows `AuthorizationStatusUpdated` (scope=some, status=Suspended) + `authorizationDesiredTaskStatusUpdatedAt/By` set on the identifier.
UAT-UKCOPO-113 · Task-level `authorizationDesiredTaskStatus = "Completed"` (per-task terminal-success)
Case: LNS-2026-00160 · Persona: RS · Stage: Collection · Case shape: GB / National / COPO Order · 1 Consumer identifier · job already delivered
Capability validated: Per-task terminal-success signal — chip rendered in success green, `taskStatus` NOT mutated by IA push.
Preconditions: (1) Open `LNS-2026-00160` and seed the single identifier with a delivered job in CollectionTracker.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Fire IA Form 4 with status `Completed`, scope `some` (target the single identifier).
2 | Inspect the page-top alert zone. |  | No case-level banner mounts.
3 | Inspect the PlanReviewTable's "Authorization" column. |  | Per-identifier chip renders `"Completed"` in success (green) Fluent color.
4 | Inspect the identifier's `taskStatus` field. |  | `taskStatus` unchanged by IA push — only `authorizationDesiredTaskStatus` mutated.
5 | Inspect the audit thread. |  | Audit thread shows `AuthorizationStatusUpdated` (scope=some, status=Completed).
UAT-UKCOPO-114 · Task-level `authorizationDesiredTaskStatus = "Cancelled"` (per-task terminal-disrupt, scope=some)
Case: LNS-2026-00160 · Persona: RS · Stage: Collection · Case shape: GB / National / COPO Order · 1 Consumer identifier · job mid-Collection
Capability validated: Per-task cancellation — the canonical contrast against case-level Cancelled (UAT-UKCOPO-102). Chip renders danger red, case-level field is CLEARED to `""`, `cancellationLocked` remains false, non-listed identifiers continue normally.
Preconditions: (1) Open `LNS-2026-00160` and seed the single identifier with a Started job in CollectionTracker.
Test Step # | Steps To Perform Test | Tester | Expected Results | Pass/Fail? | Date Tested | Query & Inputs (Only if Fail) | Related User Story | Bug ID, as a point of reference
1 | Fire IA Form 4 with status `Cancelled`, scope `some` (target the single identifier).
2 | Inspect the page-top alert zone. |  | No case-level `AuthorizationStatusBanner` mounts (scope=some clears the case-level field).
3 | Inspect the PlanReviewTable's "Authorization" column. |  | Per-identifier chip renders `"Cancelled"` in danger (red) Fluent color — "disruption-tier" state.
4 | Confirm `formData.authorizationDesiredStatus` is cleared to `""`. |  | `formData.authorizationDesiredStatus === ""`; `authorizationStatusUpdatedAt/By` zeroed.
5 | Hover Package and Deliver buttons in CollectionTracker. |  | Package and Deliver remain enabled (`cancellationLocked === false`). No tooltip gate.
6 | Inspect the identifier's `taskStatus`. |  | `taskStatus` NOT flipped to `"Cancelled"` — only `authorizationDesiredTaskStatus` mutated. The actual block enforcement for EA-Partial-GFR-blocked tasks lives in `groundsForRefusal.ts` consumers; pure IA-driven per-task Cancelled is informational + auditable.
7 | Inspect the audit thread. |  | Audit thread shows `AuthorizationStatusUpdated` (scope=some, status=Cancelled) + `authorizationDesiredTaskStatusUpdatedAt/By` recorded on the identifier. Pass criteria: • Per-task red chip displayed; no case-level banner. • Case-level field cleared. • `cancellationLocked === false`; Package + Deliver still enabled. • `taskStatus` untouched. • Audit captures both event + per-identifier timestamp.